## Sheet1
BUG TEMPLATE
BUG ID | BUG TITLE | PARAMETERS | DATE REPORTED | REPORTER | APPLICATION | MODULE | PLATFORM/OS | SEVERITY | PRIORITY | RESOLUTION | ENVIRONMENT | ATTACHMENTS | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | ASSIGNED TO | ASSIGNED AT | STATUS
#BG-01 | Profile Icon-"My profile" option is not redirecting to profile page |  | 21-2-2024 | DIVYA METTU | SINTEL | Demand Managment Page | WINDOWS | High | p1 | 1920X1810 | QA | BUG1SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to right corner of the "Demand Management Page" 2.Click on profile icon and select the"My Profile" option | By clicking on "My Profile" option the user should be redirected to the profile page | By clicking on "My Profile" option the user is not getting any changes in the application
#BG-02 | Profile Icon- In "Switch Role" drop box the "Role1" option is not present |  | 21-2-2024 | DIVYA METTU | SINTEL | Demand Managment Page | WINDOWS | High | p2 | 1920X1810 |  | BUG2SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to right corner of the "Demand Management Page" 2.Click on profile icon and select the"SwitchRole" option | In "Switch Role" Drop Box the user should also have "Role 2" option in it. | In "Switch Role" Drop Box the user sdoes not have "Role 2" option in it.
#BG-03 | Profile Icon- In "Switch Role" drop box the user is not able to change his role, "Admin","Analyst","Role-2","Role3" options are not working. |  | 21-2-2024 | DIVYA METTU | SINTEL | Demand Managment Page | WINDOWS | High | p1 | 1920X1810 |  | #bug3.mp4 | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to right corner of the "Demand Management Page" 2.Click on profile icon and select the"SwitchRole" option and select options in dropbox | In "Switch Role" Drop Box the user should be able to select his role. | In "Switch Role" Drop Box the is not able to select his role.
#BG-04 | Profile Icon-"User Preferences" option is not working |  | 21-2-2024 | DIVYA METTU | SINTEL | Demand Managment Page | WINDOWS | High | p2 | 1920X1810 |  | BUG4SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to right corner of the "Demand Management Page" 2.Click on profile icon and select the"User Preferences" option | When the user clicks on "User Preferences" option preferences should be shown | When the user clicks on "User Preferences" option the application is not showing anything.
#BG-05 | Profile Icon-"Logout" option is not working correct way. |  | 21-2-2024 | DIVYA METTU | SINTEL | Demand Managment Page | WINDOWS | High | p2 | 1920X1810 |  | #bug5.mp4 | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to right corner of the "Demand Management Page" 2.Click on profile icon and select the"Logout" option | When the user clicks on "LogOut "option the application should complety logout | When the user clicks on "LogOut "option the application is just coming out of that particular page
#BG-06 | Notification icon-Not showing any fuctionality |  | 21-2-2024 | DIVYA METTU | SINTEL | Demand Managment Page | WINDOWS | High | p2 | 1920X1810 | QA | BUG6SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to right corner of the "Demand Management Page" 2.Click on navigation icon . | The notification icon is expected to show the notifications of the application | The notification icon is not showing any notifications by clicking on it.
#BG-07 | Consistency-"Consistency","Inbound","Outbound","Missed Releases","Delivery Forecast", "Delivery JIT" count is shown as "0". |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG7SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box. 4.Click on Navigation option | The number of "Consistency","Inbound","Outbound","Missed Releases", "Delivery Forecast", "Delivery JIT" should be shown | The number of "Consistency","Inbound","Outbound","Missed Releases" ,"Delivery Forecast", "Delivery JIT" is shown as "0".
#BG-08 | Delivery Forest- A "i" icon beside "Delivery Forecast" in consistency of release validation is not working. | 1.In bound Screen 2.Out Bound Screen 3.Missed Releases Screen 4.Phase out probability screen(all,not read) 5.Max demand results 6.Forecast snapshot screen | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG8SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency". 4.Click on i icon beside "Demand Forest" | The "i" icon should show the information regarding the "Delivery Forest" | The "i" icon should is not showing any information on clicking on it.
#BG-09 | Delivery Forest Data Box- The "View Delivery Forecast" option in the three dots is not working | 1.Consistency inbound screen 2.Phase out probabilty all screen | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG9SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency". 4.Click on 3 dots on right end of the page and select "view Delivery Forecast" | The "View Delivery Forecast" option should show the delivery fore cast | The "View Delivery Forecast" option is not working.
#BG-10 | Delivery Forest Data Box- The "View Details" option in the three dots is not having any information |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG10SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency". 4.Click on 3 dots on right end of the page and select "view Details" | The "View Details" option should show information about that customer | The "View Details" option is showing an empty page with no information
#BG-11 | Filter Name- The first filter should be named as "Status" | 1.In bound Delivery Forecast Screen 2.In bound Delivery Jit Screen 3.Missed Releases with control screen. | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p3 | 1920X1810 | QA | BUG11SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency". 4.Navigate to filter block and check first option | The filter name should be status as it's for status | The filter name is not mentioned as the Status
#BG-12 | Clear option-The"Clear Option" in Filters block of Delivery Forecast is not working properly in inbound | 1In bound Delivery Forecast Screen 2.In bound Delivery Jit Screen 3.Missed Releases with control screen 4.Missed Release withput control 5.OutBound Screen 6.Phase out probability all screen | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | High | p2 | 1920X1810 |  | BUG12SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency". 4.Navigate to filter block and check first option | The "Clear" option should clear all the entries in the application | The "Clear" option is not clearing all entries in the filter
#BG-13 | Filter Name-The second filter name should be "Date" | 1In bound Delivery Forecast Screen 2.In bound Delivery Jit Screen | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG13SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency". 4.Navigate to filter block and check secoond option | The second filter name should be "Date" as it is giving information about "Date" | The Second filter name is not given anything by default it is mentioned as a date
#BG-14 | View Delivery Jit-The option "View Delivery Jit" in delivery jit of in bound is not working |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG14SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency" and navigate to Delivery JIT option 4.Click on 3 dots on right end of the page and select "view Details" | The "Delivery JIT" option should show the info about delivery jit | The "Delivery JIT" option is not showing any information
#BG-15 | Edit ASN-In out bound of consistency we are not able to edit the series |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-CONSISTENCY | WINDOWS | Medium | p2 | 1920X1810 |  | BUG15SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "consistency" and navigate to outbound option 4.Click on 3 dots on right end of the page and select edit option | In edit ASN all the options should be available to edit the ASN | The Series option is blocked to change
#BG-16 | FILTERS- The filters option in phase of probability are getting applied before clicking on apply button | 1.Phase out probability all screen 2.Phase out probability Not Read Screen 3.Consistency page | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-Phase out probability | WINDOWS | Low | p3 | 1920X1810 | QA | #bug16.mp4 | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "Phase out Probability". 4.Navigate to filter block and select options | Filters should be applied after clicking on apply button | Filters are getting applied before clicking on apply button
#BG-17 | Mark As -The "MarkAs" application is getting blocked when all the applications are selected at a time. |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-Phase out probability | WINDOWS | Medium | p2 | 1920X1810 |  | BUG17SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "Phase out probability". 4.Navigate to data and select all and click on mark as option | "Mark As" option should be available after selecting all the applications at a time | Mark As' option is getting blocked when all the applications are selected
#BG-18 | Details-When selected details with three dots in the application we are getting a warning details are not available |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-Phase out probability | WINDOWS | Low | p3 | 1920X1810 |  | BUG18SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "Phase out probability". 4.Select the 3 doots in right corner and click on "details" | When clicked on "Details" we should get redirected to the details | We are getting a warning that no details are available
#BG-19 | Apply-Apply option box is out of filter box |  | 21-2-2024 | DIVYA METTU | SINTEL | Release Validation-Max Demand Limit | Windows | Low | p3 | 1920X1810 |  | BUG19SCREENSHOT | Prerequsite-Login to "Sintel" Application In "ALL" option "my Organizations" should be selected In "ABC Company" 'View DM" hyperlink should be opened and "Demand Management " page in it has to be opened. 1.Navigate to the profile icon and select "Logout" option 2.Again click on the "View DM" hyper link in"ABC Company". 3.Navigate to release "RELEASE MANAGEMENT" and click on "Release Validation" drop box and open "Max Demand Limit". 4.Navigate to the "filter" box and move towards apply button
#BG-20
#BG-21